## Sheet1
Date | Start | End | Break | Total mins/hrs | Description |  | Estimated time taken | Adjusted estimate
2020-03-28 | 11:13 | 12:03 | 0:00 | 0:50 | A movement scrip that allows the player to move around in an isometric world with forward backward and side way movement being dependent on whatever way the camera is faceing. | Script tutorals used: https://www.youtube.com/watch?v=XhliRnzJe5g&t=1s | 0:35 | 0:50
2020-03-29 | 13:26 | 16:37 | 0:06 | 3:11 | A script that allows a person to switch an obect with another one by clicking on the object that they want, and then proceeding to click on an empy area to then place that object . |  | 1:30 | 3:11
2020-03-31 | 10:14 | 12:58 | 0:11 | 2:44 | A script that manages were the obects will be placed on the grid and when pressing a button on screen will expand the grid by 1 section outwards. |  | 1:00 | 2:44
2020-04-03 | 13:06 | 15:41 | 0:35 | 2:35 | Was going over the scripts I have already created and adding some assets to the scene to try and make it make sense from a gameplay perspective.