## Sheet1
Programming Task Log
Component No. | Component Name: | Task | Date | Baseline Estimate Time/H | Start | End | Break/H | Actual Time/H | Total Actual Time/H | Total Estimated Time/H | Hours worked on task/H | Correction Factor | Adjusted Estimate Time/H
1 | Colour Changing | A script which enables an item to change colour | 2020-02-18 | 1 | 16:00 | 16:30 | 0 | 0.5 | 0.5 | 1 | 0.5 | 50% | 0.5
1 | Colour Changing | A 3D movement script | 2020-02-20 | 0.5 | 14:00 | 14:15 | 0 | 0.25 | 0.25 | 0.5 | 0.25 | 50% | 0.25
1 | Colour Changing | A 1st Person Camera Controller | 2020-02-20 | 1 | 14:20 | 14:50 | 0 | 0.5 | 0.5 | 1 | 0.5 | 50% | 0.5
1 | Colour Changing | A ‘Mirror’/Reflective Component | 2020-02-21 | 2 | 14:00 | 14:15 | 0 | 0.25 | 0.25 | 2 | 0.25 | 12.5% | 0.25
2 | 2D Wall Jump and Movement | A 2DWall Jump and Movement Script | 2020-02-25 | 2 | 16:00 | 20:00 | 2 | 4 | 6 | 2 | 4 | 200% | 4
3 | UI Drag and Drop | A UI Drag and Drop Script | 2020-03-03 | 1 | 16:00 | 16:45 | 0 | 0.75 | 0.75 | 1 | 0.75 | 75% | 0.75
4 | Character Switch | Allows the player to switch control between multiple characters | 2020-03-17 | 1 | 11:00 | 11:30 | 0 | 0.5 | 0.5 | 1 | 0.5 | 50% | 0.5
1 | Colour Changing | Switched the colour changing component from 3D to 2D, removed other 3D components | 2020-03-24 | 0.5 | 15:00 | 15:15 | 0 | 0.25 | 0.25 | 0.5 | 0.25 | 50% | 0.25
Final | Small Programming Game Project | Created the final game | 2020-04-14 | 2 | 14:00 | 17:00 | 0 | 3 | 3 | 2 | 3 | 150% | 3