## Sheet1
Michelle Snowball
Programming Task Log - Semester 2
| Task | Date | Baseline estimate in minutes | Start | End | Interruptions | Measured time in minutes | Correction factor | Adjusted estimate
| watch and follow brackey's tutorial | Feb. 25th | 30 | 14:28 | 15:30 | 10 min | 50 | 1.6667 | 50
| make basic character controller | March 5th | 30 | 16:00 | 16:30 | 5 min. | 25 | 1.25 | 37.5
| make dust particle generator | March 5th | 60 | 16:30 | 17:46 | 20 min. | 56 | 1.0917 | 65.5
| Make Ai follow paths | March 9th | 30 | 5:00 | 5:45 | 10 mins | 35 | 1.1067 | 33.2
| Add time rewinding | March 9th | 60 | 7:00 | 8:30 | 10 mins | 80 | 1.1714 | 70.2857
| Set up character movement for homing missiles | March 15th | 5 | 18:50 | 19:06 | 3 min. | 13 | 1.2047 | 6.0233
| watch and follow brackey's tutorial - homing missiles | March 15th | 45 | 19:07 | 19:36 | 0 | 29 | 1.1077 | 49.8462
| Add followStrength to make missiles dodge-able | March 20th | 15 | 12:10 | 12:55 | 5 min. | 40 | 1.1927 | 17.8909