## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sheet1
| Table 1 | Sheet1

## Sheet1
Task | Date | Baseline estimate | Start | End | Interruptions | Measured time | Correction factor | Adjusted estimate
2D to 3D Camera | 2020-03-28 | 4 | 43966.7083 | 43966.7917 | 0 | 2 | 50% | 2
Enemy Fire | 2020-04-07 | 2 | 43966.5625 | 43966.7083 | 0 | 3.5 | 91.67% | 1.8333
Multi Jump | 2020-04-20 | 5 | 43966.6667 | 43966.875 | 0 | 5 | 95.45% | 4.7727
Coin Collect | 2020-05-06 | 3 | 43966.7083 | 43966.8333 | 0 | 3 | 95.45% | 2.8636
Final Game Project | 2020-05-14 | 3 | 43966.8333 | 43966.9583 | 0 | 3 | 95.45% | 2.8636