## Sheet1
Task | Estimated Time of Completion | Date Started | Time of Day That I Started at | Time of Day I finished at | Length of any Interruptions | Time Taken to Complete task (Minutes) | Estimation Error-(PercentageBased) | Additional Notes
HealthBar | 1Hour | 2020-03-27 | 10:36am | 11:12am | 15minutes | 34.5 | 28% | I'll have to admit creating a healthbar seems slightly complex and yet it is somewhat simple to understand and implament with time